## Sheet1
[6 empty] | Week 1 | [5 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7
# | Task/Event |  |  | Prereq | Person in Charge | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S
1 | Tournament milestone |  |  |  | All | bar: Week 7 S
2 | Doc Submission 1 milestone |  |  |  | Fred | bar: Week 2 W
3 | Doc Submission 2 milestone |  |  |  | Mary | bar: Week 4 W
4 | Doc Submission 3 milestone |  |  |  | Joe | bar: Week 7 W
5 | Conception
5.1 |  | Go over rules |  |  | sally, Alan, Fred | bar: Week 1 M
5.2 |  | Determine Game requirements |  |  | Mary, Joe, Jim | bar: Week 1 M
5.3 |  | Present Game specifications |  | 5.1, 5.2 | sally, Alan, Fred, Mary, Joe, Fred | bar: Week 1 T
5.4 |  | Idea Generation |  | 5.3 | All | bar: Week 1 W to Week 1 F
5.5 |  | Concept extension |  | 6.1 | All | bar: Week 2 T
6 | Evaluation
6.1 |  | Initial concept selection |  | 5.4 | All | bar: Week 1 S
6.2 |  | Model top 3 ideas |  | 5.4 | All divided into 3 groups | bar: Week 1 S to Week 2 T
6.3 |  | Presentation of ideas |  |  | Rep from each group | bar: Week 2 T
6.4 |  | Final concept selection |  | 6.3 | All | bar: Week 2 W
7 | Implementation |  |  | 6.4
7.1 |  | Mechanical construction Bot 1 |  |  | Fred
7.1.1 |  |  | Mobility |  | Mary | bar: Week 2 R to Week 3 R
7.1.2 |  |  | Manipulation |  | Kim | bar: Week 2 R to Week 3 R
7.2 |  | Mechanical construction Bot 2 |  |  | Alice
7.2.1 |  |  | Mobility |  | Joe | bar: Week 2 R to Week 3 R
7.2.2 |  |  | Manipulation |  | Sally | bar: Week 2 R to Week 3 R
7.3 |  | Software Bot 1 |  |  | Pat
7.3.1 |  |  | Navigation |  | Jim | bar: Week 2 R to Week 3 R
7.3.2 |  |  | Part gathering |  | Mako | bar: Week 2 R to Week 3 R
7.3.3 |  |  | Part placement |  | Chandra | bar: Week 2 R to Week 3 R
7.4 |  | Software Bot 2 |  |  | Anish
7.4.1 |  |  | Navigation |  | Ben | bar: Week 2 R to Week 3 R
7.4.2 |  |  | Part gathering |  | Susann | bar: Week 2 R to Week 3 R
7.4.3 |  |  | Part placement |  | Julie | bar: Week 2 R to Week 3 R
7.5 |  | Integration Bot 1 |  | 7.1, 7.3 | Fred, Pat | bar: Week 3 S to Week 4 W
7.6 |  | Integration Bot 2 |  | 7.2, 7.4 | Anish, Alice | bar: Week 3 S to Week 4 W
7.7 |  | Integration of robot team |  | 7.5, 7.6 | … | bar: Week 4 R to Week 5 M
7.8 |  | Testing |  |  | …
7.8.1 |  |  | Seeding Test | 7.5, 7.6 | … | bar: Week 5 S to Week 5 W
7.8.2 |  |  | Head to Head tests | 7.5, 7.6 | … | bar: Week 5 S to Week 5 W
7.9 |  | Mechanical construction Bot 1B |  | 7.5, 7.6 | …
7.9.1 |  |  | Mobility |  | …. | bar: Week 5 M to Week 5 F
7.9.2 |  |  | Manipulation |  | … | bar: Week 5 M to Week 5 F
7.10 |  | Mechanical construction Bot 2B |  | 7.5, 7.6 | …
7.10.1 |  |  | Mobility |  | … | bar: Week 5 M to Week 5 F
7.10.2 |  |  | Manipulation |  | … | bar: Week 5 M to Week 5 F
7.11 |  | Software Bot 1B |  | 7.5, 7.6 | …
7.11.1 |  |  | Navigation |  | … | bar: Week 5 T to Week 5 S
7.11.2 |  |  | Part gathering |  | … | bar: Week 5 T to Week 5 S
7.11.3 |  |  | Part placement |  | … | bar: Week 5 T to Week 5 S
7.12 |  | Software Bot 2B |  | 7.5, 7.6 | …
7.12.1 |  |  | Navigation |  | … | bar: Week 5 T to Week 5 S
7.12.2 |  |  | Part gathering |  | … | bar: Week 5 T to Week 5 S
7.12.3 |  |  | Part placement |  | … | bar: Week 5 T to Week 5 S
7.13 |  | Integration Bot 1 |  | 7.8, 7.9, 7.11 | … | bar: Week 6 M to Week 6 R
7.14 |  | Integration Bot 2 |  | 7.8, 7.10, 7.12 | … | bar: Week 6 M to Week 6 R
7.15 |  | Integration of robot team |  | 7.9, 7.10, 7.11, 7.12 | … | bar: Week 6 W to Week 7 S
7.16 |  | Testing |  |  | …
7.16.1 |  |  | Seeding Test | 7.13, 7.14 | … | bar: Week 7 S to Week 7 W
7.16.2 |  |  | Head to Head tests | 7.13, 7.14 | … | bar: Week 7 S to Week 7 W
8 |  | Team Website Updates |  |  | Chris, Clancy | bar: Week 1 F; Week 2 W; Week 3 M; Week 3 S; Week 4 R; Week 5 T; Week 6 S; Week 6 F; Week 7 W; Week 7 S
|  |  |  | Key: | Fixed milestone | bar: Week 1 M
Scheduled task | bar: Week 1 M
Behind schedule | bar: Week 1 M
Ahead of schedule | bar: Week 1 M