## Team_130_Plan
TEAM 130 2007 SCHEDULE
Adult Advisors: Bob Ekman, Paul Newell
Team members | Bot 1 | Bot 2 | Bot 3 | Bot 4
Stephen Carlson | Roger Ding | Ashish Shenoy | Stephen Carlson | Elwin Wang (Doc)
Roger Ding | Chris Emr (Doc)* | Brian Zhang (Doc) | Justin Gura (Doc)
Chris Emr | Chris Hogan (Doc) |  | Daniel Lu
Justing Gura | Eliot Rudnick-Cohen
Chris Hogan
Daniel Lu
Eliot Rudnick-Cohen
Ashish Shenoy (Team Leader)
Elwin Wang
Brian Zhang (Team Leader, Documentation Lead)
* (Doc) stands for Documentation; this person contributes raw information to the Documentation Lead
Week 1
Goals | Responsible | Milestone | Status | Notes
Build Game Board | Paul Newell
| ALL | 2007-03-22 | Complete On Time | the board in the promo video was wrong
Learn Game Rules (watch promo video) | ALL | 2007-03-22 | Complete On Time
Inventory Kit | Roger, Chris E, Chris H | 2007-03-29 | Complete On Time
Check FAQ | Brian, Ashish | 2007-03-22 | Complete On Time | infinite water?? careful with the diction
Initial Designs | ALL | 2007-03-29 | Complete On Time
Week 2
Goals | Responsible | Milestone | Status | Notes
Create Groups | Group 1, Group 2, Group 3, Group 4 | 2007-03-29 | Complete On Time | not sure about Elwin working alone
Study Game Board | Group 1, Group 2, Group 3, Group 4 | 2007-03-29 | On-going - Incomplete | static robot design possible
Discuss Designs | Group 1, Group 2, Group 3, Group 4 | 2007-03-31 | On-going - Incomplete
Begin Models | Group 1, Group 2, Group 3, Group 4
Study Past Code | Justin, Stephen | 2007-03-31 | On-going - Incomplete
Study Past Model | Roger, Chris E, Chris H, Eliot | 2007-03-31 | On-going - Incomplete
Begin Construction | Group 1, Group 2, Group 3, Group 4 | 2007-03-31 | On-going - Incomplete | team members are very excited
Gathering Materials | Roger, Eliot
Bot 1 construction | Roger, Chris E, Chris H, Eliot | 2007-03-31 | On-going - Incomplete
Bot 2 construction | Ashish | 2007-03-31 | On-going
Bot 3 construciton | Justin, Daniel | 2007-03-31 | On-going
Bot 4 construction | Elwin | 2007-03-31 | On-going
Documentation | Justin, Elwin, Brian | 2007-03-31 | Complete
Week 3
Goals | Responsible | Milestone | Status | Notes
Study Past Code | Justin, Stephen | 2007-04-02 | Complete
Study Past Model | Roger, Chris E, Chris H, Eliot | 2007-04-02 | Complete
Evaluate Designs | Group 1, Group 2, Group 3, Group 4 | 2007-04-05 | Complete | rejected two designs
Construction - bases, arms, etc | Group 1, Group 2, Group 3, Group 4 | 2007-04-07
Gathering Materials | Roger, Eliot | 2007-04-07 | Complete
Bot 1 construction | Roger, Chris E, Chris H, Eliot | 2007-04-07 | On-going - Incomplete
Bot 2 construction | Ashish | 2007-04-07 | On-going - Incomplete
Bot 3 construciton | Justin, Daniel, Stephen | 2007-04-07 | On-going - Incomplete
Bot 4 construction | Elwin | 2007-04-07 | On-going - Incomplete
Programming - start basic programming - movement | Group 1, Group 2, Group 3, Group 4 | 2007-04-07
setup IC | Brian, Ashish, Stephen | 2007-04-07 | Complete
Bot 1 code | Brian | 2007-04-07 | Behind Schedule | we really need to get moving
Bot 2 code | Brian, Ashish | 2007-04-07 | Behind Schedule
Bot 3 code | Stephen, Justin | 2007-04-07 | On-going - Incomplete
Bot 4 code | Brian | 2007-04-07 | Behind Schedule
Integrating Bot 1 & Bot 2 | Group 1, Group 2 | 2007-04-07
mobility | Roger, Chris E, Chris H, Brian, Ashish | 2007-04-07 | On-going - Incomplete
scoring | Ashish | 2007-04-07 | Behind Schedule
Integrating Bot 2 & Bot 3 | Group 2, Group 3 | 2007-04-07
mobility | Brian, Ashish, Stephen, Justin, Daniel | 2007-04-07 | On-going - Incomplete
scoring | Ashish | 2007-04-07 | Behind Schedule
Integrating Bot 2 & Bot 4 | Group 2, Group 4 | 2007-04-07
mobility | Brian, Ashish, Elwin | 2007-04-07 | Behind Schedule
scoring | Ashish | 2007-04-07 | Behind Schedule
Documentation | Justin, Elwin, Brian | 2007-04-07 | Complete
Week 4
Goals | Responsible | Milestone | Status | Notes
Evaluate Designs | Group 1, Group 2, Group 3, Group 4 | 2007-04-12
Construction | Group 1, Group 2, Group 3, Group 4 | 2007-04-14
Bot 1 construction | Roger, Chris E, Chris H, Eliot | 2007-04-14
Bot 2 construction | Ashish | 2007-04-14
Bot 3 construciton | Justin, Daniel | 2007-04-14
Bot 4 construction | Elwin | 2007-04-14
Programming | Group 1, Group 2, Group 3, Group 4 | 2007-04-14
Bot 1 code | Brian | 2007-04-14
Bot 2 code | Brian, Ashish | 2007-04-14
Bot 3 code | Stephen, Justin | 2007-04-14
Bot 4 code | Brian | 2007-04-14
Integrating Bot 1 & Bot 2 | Group 1, Group 2 | 2007-04-14
mobility | Roger, Chris E, Chris H, Brian, Ashish | 2007-04-14
scoring | Ashish | 2007-04-14
Integrating Bot 2 & Bot 3 | Group 2, Group 3 | 2007-04-14
mobility | Brian, Ashish, Stephen, Justin, Daniel | 2007-04-14
scoring | Ashish | 2007-04-14
Integrating Bot 2 & Bot 4 | Group 2, Group 4 | 2007-04-14
mobility | Brian, Ashish, Elwin | 2007-04-14
scoring | Ashish | 2007-04-14
Documentation | Justin, Elwin, Brian | 2007-04-14
Week 5
Goals | Responsible | Milestone | Status | Notes
Evaluate Designs | Group 1, Group 2, Group 3, Group 4 | 2007-04-19
Construction | Group 1, Group 2, Group 3, Group 4 | 2007-04-21
Bot 1 construction | Roger, Chris E, Chris H, Eliot | 2007-04-21
Bot 2 construction | Ashish | 2007-04-21
Bot 3 construciton | Justin, Daniel | 2007-04-21
Bot 4 construction | Elwin | 2007-04-21
Programming | Group 1, Group 2, Group 3, Group 4 | 2007-04-21
Bot 1 code | Brian | 2007-04-21
Bot 2 code | Brian, Ashish | 2007-04-21
Bot 3 code | Stephen, Justin | 2007-04-21
Bot 4 code | Brian | 2007-04-21
Integrating Bot 1 & Bot 2 | Group 1, Group 2 | 2007-04-21
mobility | Roger, Chris E, Chris H, Brian, Ashish | 2007-04-21
scoring | Ashish | 2007-04-21
Integrating Bot 2 & Bot 3 | Group 2, Group 3 | 2007-04-21
mobility | Brian, Ashish, Stephen, Justin, Daniel | 2007-04-21
scoring | Ashish | 2007-04-21
Integrating Bot 2 & Bot 4 | Group 2, Group 4 | 2007-04-21
mobility | Brian, Ashish, Elwin | 2007-04-21
scoring | Ashish | 2007-04-21
Documentation | Justin, Elwin, Brian | 2007-04-21
Week 6
Goals | Responsible | Milestone | Status | Notes
Evaluate Designs | Group 1, Group 2, Group 3, Group 4 | 2007-05-03
Programming | Group 1, Group 2, Group 3, Group 4 | 2007-05-05
Bot 1 code | Brian | 2007-05-05
Bot 2 code | Brian, Ashish | 2007-05-05
Bot 3 code | Stephen, Justin | 2007-05-05
Bot 4 code | Brian | 2007-05-05
Integrating Bot 1 & Bot 2 | Group 1, Group 2 | 2007-05-05
mobility | Roger, Chris E, Chris H, Brian, Ashish | 2007-05-05
scoring | Ashish | 2007-05-05
Integrating Bot 2 & Bot 3 | Group 2, Group 3 | 2007-05-05
mobility | Brian, Ashish, Stephen, Justin, Daniel | 2007-05-05
scoring | Ashish | 2007-05-05
Integrating Bot 2 & Bot 4 | Group 2, Group 4 | 2007-05-05
mobility | Brian, Ashish, Elwin | 2007-05-05
scoring | Ashish | 2007-05-05
Testing
Bot 1 test
Bot 2 test
Bot 3 test
Bot 4 test
Documentation | Justin, Elwin, Brian | 2007-05-05
Week 7
Goals | Responsible | Milestone | Status | Notes
Evaluate Designs | Group 1, Group 2, Group 3, Group 4 | 2007-05-03
Programming | Group 1, Group 2, Group 3, Group 4 | 2007-05-05
Bot 1 code | Brian | 2007-05-05
Bot 2 code | Brian, Ashish | 2007-05-05
Bot 3 code | Stephen, Justin | 2007-05-05
Bot 4 code | Brian | 2007-05-05
Integrating Bot 1 & Bot 2 | Group 1, Group 2 | 2007-05-05
mobility | Roger, Chris E, Chris H, Brian, Ashish | 2007-05-05
scoring | Ashish | 2007-05-05
Integrating Bot 2 & Bot 3 | Group 2, Group 3 | 2007-05-05
mobility | Brian, Ashish, Stephen, Justin, Daniel | 2007-05-05
scoring | Ashish | 2007-05-05
Integrating Bot 2 & Bot 4 | Group 2, Group 4 | 2007-05-05
mobility | Brian, Ashish, Elwin | 2007-05-05
scoring | Ashish | 2007-05-05
Testing
Bot 1 test
Bot 2 test
Bot 3 test
Bot 4 test
Documentation | Justin, Elwin, Brian | 2007-05-05
Presentation | Justin, Elwin, Brian | 2007-05-12
Week 8
Goals | Responsible | Milestone | Status | Notes
Evaluate Designs | Group 1, Group 2, Group 3, Group 4 | 2007-05-03
Testing
Bot 1 test
Bot 2 test
Bot 3 test
Bot 4 test
Documentation | Justin, Elwin, Brian | 2007-05-05
Presentation | Justin, Elwin, Brian | 2007-05-12