## Sheet1
Explorer Post 1010 Botball Team 0129
Team Members: |  | Documentation: | Building: | Coding:
Kevin Heithaus | Terry Sifrit | Kevin Heithaus | Misha Shangold | Dana Reback
Misha Shangold | Brandon Nishan | Arleen Thukral | Stuart Brothers | Jay Koby
Arleen Thukral | David Wikman |  | David Wikman | Zachary Baer
Jay Koby | Zachary Baer |  | Misha Shangold | Alex Silvey
Stuart Brothers | Alex Silvey |  | Robert Chatterson
Robert Chatterson | Dana Reback |  | Terry Sifrit
| James Brent |  | James Brent
Milestones/Tasks | Assignment | Day | Status | Notes
Week 1:
Build Game Board | Bob Ekman, Sponsor | 2007-03-21 | Complete | Thanks Bob and Paul!
Learn Game Rules | All | 2007-03-19 | Complete | Interesting game this year.
Concept Ideas
Record concept ideas | Kevin, Arleen, Dana | 2007-03-19 | Complete
Botball Doc. site - assignment | Kevin | Through 07-Apr-07 | Complete
Project Plan | Kevin | 2007-03-31 | Complete
Brainstorming Ideas | All | 2007-03-19 | Complete | Lots of good ideas from all.
Week 2:
Documentation | Kevin, Arleen | 2007-03-28 | Complete
Construction
Bot 1 Building | David, Misha | 2007-03-28 | Incomplete, will continue
Bot 2 Building | Robert, Zach | 2007-03-31 | Design stage
Sensor Experimentation |  |  |  | Checking to make sure that sensors can pick up tribbles and houses
Sonar Testing | Jay, Brandon | 2007-03-28 | Complete
Camera Testing | Misha, Stuart | 2007-03-28 | Complete
Experimentation |  |  |  | Mostly with tribble sorting, still not sure if we can devote this many people to random concepts
Tribble Sorting | Terry, Dana | 28/31-Mar-07 | Incomplete, next week
Water Claw | Misha | 2007-03-31 | Complete
Week 3: |  |  |  | We made effective use of spring break by coming in and completing construction on both bots
Documentation | Kevin | 2007-04-04 | Complete
Construction
Bot 1 House Mechanism | David | 2007-04-02 | Complete
Bot 1 Chassis | Stuart | 2007-04-02 | Incomplete | Need this to be done to begin testing the house bot
Bot 2 Water Claw | Misha | 2007-04-04 | Complete | Will test on Friday for feasibility
Bot 2 Chassis | James | 2007-04-02 | Incomplete, will finish Weds
Coding
Simulation for Bot 1 | Dana
Sensor Testing | Jay | 2007-04-04 | Incomplete | Sonar is causing problems
Test code for Bot 2 | Alex | 2/4-Apr-07 | Complete | Will load code and test on Saturday
Team Progress Meeting | All | 2007-04-07 |  | Good ideas, reassessed the plans we originally made. Rejected some ideas, less experimentation
Week 4: |  |  |  | As we began to code, we faced difficulties with navigation with respect to getting House Mechanism Bot over the PVC pipe
Documentation | Kevin, Arleen | 2007-04-11 | Complete
Coding
Sensor Experimentation | Jay, Alex | 2007-04-11 | Incomplete | Hopefully we'll finally figure out our sonar problems
Bot 1 Coding | Zach | 2007-04-14 | Incomplete | Bot 1 is done, just testing mechanism
Bot 2 Coding | Dana | 2007-04-14 | Incomplete
Building
Bot 1 Chassis | Stuart | 2007-04-11 | Incomplete | When the chassis (for both bots) are finished, we can load up some code and get our sensor navigation down
Bot 2 Chassis | James | 2007-04-11 | Incomplete
Experimentation
Tribble Mechanism | Kevin, Terry | 2007-04-14 | Incomplete | On the 14th we will determine if we continue the testing
Team Progress Meeting | All | 2007-04-07 |  | Not everyone is able to participate in all the meetings because of other commitments (school plays, family events, homework)
Week 5:
Coding
Bot 1 Code | Stuart, | 2007-04-18 | Complete | We submtted the code design for documentation
Bot 2 Code | Dana, Jay | 2007-04-18 | Incomplete | We submtted the code design for documentation
Building
Refining Bot 1 | Misha | 2007-04-18 | Complete | We made minor modifications with detachable arm and senory equipment.
Refining Bot 2 | David, James | 2007-04-18 | Complete
Update Project Plan | Kevin, Arleen | 2007-04-21 | Complete | Submitted
Experimentation
Test robot on gameboard | Terry | 2007-04-21 | Incomplete | Taking notes on what to change. We don't have any scoring data yet.
Team Progress Meeting | All | 2007-04-21 |  | As a result of trepidation for AP exams, we are facing difficulties with participation as many members could not find time to participate. Still we made progress this week.
Week 6:
Documentation | Kevin, Arleen, Dana | 2007-04-23
Testing
Bot 1 Testing | Misha, James | 2007-04-23
Bot 2 Testing | Stuart, Terry | 2007-04-23
Design Refinement | Build Team
Bot 1 Refinement |  | 2007-04-25
Bot 2 Refinement |  | 2007-04-25
Coding | Coding Team
Bot 1 Code Writing |  | 2007-04-25
Bot 2 Code Writing |  | 2007-04-25
Team Progress Meeting | All | 2007-04-28
Week 7:
Documentation | Kevin, Arleen, Dana | 2007-04-29
Testing
Bot 1 Testing |  | 2007-04-29
Bot 2 Testing |  | 2007-04-29
Design Refinement | Build Team
Bot 1 Refinement |  | 2007-05-02
Bot 2 Refinement |  | 2007-05-02
Coding | Coding Team
Bot 1 Code Writing |  | 2007-05-02
Bot 2 Code Writing |  | 2007-05-02
Team Progress Meeting | All | 2007-05-05
Week8:
Documentation | Kevin, Arleen, Dana | 2007-05-07
Testing
Bot 1 Testing | Misha, James | 2007-05-07
Bot 2 Testing | Stuart, Terry | 2007-05-07
Design Refinement | Building Team | 2007-05-09
Bot 1 Refinement
Bot 2 Refinement
Coding | Coding Team | 2007-05-09
Bot 1 Code Writing
Bot 2 Code Writing
Tournament Presentation | Arleen, Kevin
Test and Refine All Bots/Code | All | 2007-05-11
Note on A11: Milestones will be written in bold italics and tasks will have a regular font