## Sheet1
TEAM 130 2007 SCHEDULE
Adult Advisors: Bob Ekman
Team members | Bot 1 | Bot 2 | Bot 3 | Bot 4 (rejected)
Stephen Carlson | Roger Ding | Ashish Shenoy | Stephen Carlson
Roger Ding | Chris Emr (Doc)* | Brian Zhang (Doc) | Justin Gura (Doc)
Chris Emr | Chris Hogan (Doc) | Elwin Wang | Daniel Lu
Justing Gura | Eliot Rudnick-Cohen
Chris Hogan
Daniel Lu
Eliot Rudnick-Cohen
Ashish Shenoy (Team Leader)
Elwin Wang
Brian Zhang (Team Leader, Documentation Lead)
* (Doc) stands for Documentation; this person contributes raw information to the Documentation Lead
Week 1
Goals | Responsible | Milestone | Status | Notes
Build Game Board | Bob Ekman
| ALL | 2007-03-22 | Complete | the board in the promo video was wrong
Learn Game Rules (watch promo video) | ALL | 2007-03-22 | Complete
Inventory Kit | Roger, Chris E, Chris H | 2007-03-29 | Complete
Check FAQ | Brian, Ashish | 2007-03-22 | Complete | infinite water?? careful with the diction
Initial Designs | ALL | 2007-03-29 | Complete
Week 2
Goals | Responsible | Milestone | Status | Notes
Create Groups | Group 1, Group 2, Group 3, Group 4 | 2007-03-29 | Complete | not sure about Elwin working alone
Study Game Board | Group 1, Group 2, Group 3, Group 4 | 2007-03-29 | On-going | static robot design possible
Discuss Designs | Group 1, Group 2, Group 3, Group 4 | 2007-03-31 | On-going
Begin Models | Group 1, Group 2, Group 3, Group 4
Study Past Code | Justin, Stephen | 2007-03-31 | On-going
Study Past Model | Roger, Chris E, Chris H, Eliot | 2007-03-31 | On-going
Begin Construction | Group 1, Group 2, Group 3, Group 4 | 2007-03-31 | On-going | team members are very excited
Gathering Materials | Roger, Eliot
Bot 1 construction | Roger, Chris E, Chris H, Eliot | 2007-03-31 | On-going
Bot 2 construction | Ashish | 2007-03-31 | On-going
Bot 3 construciton | Justin, Daniel | 2007-03-31 | On-going
Bot 4 construction | Elwin | 2007-03-31 | On-going
Documentation | Justin, Elwin, Brian | 2007-03-31 | Complete
Week 3
Goals | Responsible | Milestone | Status | Notes
Study Past Code | Justin, Stephen | 2007-04-02 | Complete
Study Past Model | Roger, Chris E, Chris H, Eliot | 2007-04-02 | Complete
Evaluate Designs | Group 1, Group 2, Group 3, Group 4 | 2007-04-04 | Complete | rejected two designs
Construction | Group 1, Group 2, Group 3, Group 4 | 2007-04-07
Gathering Materials | Roger, Eliot | 2007-04-07 | Complete
Bot 1 construction | Roger, Chris E, Chris H, Eliot | 2007-04-07 | On-going
Bot 2 construction | Ashish | 2007-04-07 | On-going
Bot 3 construciton | Justin, Daniel | 2007-04-07 | On-going
Bot 4 construction | Elwin | 2007-04-07 | On-going
Programming - preliminary | Group 1, Group 2, Group 3, Group 4 | 2007-04-07
setup IC | Brian, Ashish, Stephen | 2007-04-07 | Complete
Bot 1 code | Brian | 2007-04-07 | Not Started - Behind schedule
Bot 2 code | Brian, Ashish | 2007-04-07 | Not Started - Behind schedule
Bot 3 code | Stephen, Justin | 2007-04-07 | On-going
Bot 4 code | Brian | 2007-04-07 | Not Started - Behind schedule
Integrating Bot 1 & Bot 2 | Group 1, Group 2 | 2007-04-07
mobility | Roger, Chris E, Chris H, Brian, Ashish | 2007-04-07 | On-going
scoring | Ashish | 2007-04-07 | Not Started - Behind schedule
Integrating Bot 2 & Bot 3 | Group 2, Group 3 | 2007-04-07
mobility | Brian, Ashish, Stephen, Justin, Daniel | 2007-04-07 | On-going
scoring | Ashish | 2007-04-07 | Not Started - Behind schedule
Integrating Bot 2 & Bot 4 | Group 2, Group 4 | 2007-04-07
mobility | Brian, Ashish, Elwin | 2007-04-07 | Not Started - Behind schedule
scoring | Ashish | 2007-04-07 | Not Started - Behind schedule
Documentation | Justin, Elwin, Brian | 2007-04-07 | Complete
Week 4 |  |  |  | What a lovely day.
Goals | Responsible | Milestone | Status
Evaluate Designs | Group 1, Group 2, Group 3, Group 4 | 2007-04-11 | Complete
Construction | Group 1, Group 2, Group 3, Group 4 | 2007-04-14
Bot 1 construction | Roger, Chris E, Chris H, Eliot | 2007-04-14 | Complete
Bot 2 construction | Ashish | 2007-04-14 | On-going
Bot 3 construciton | Justin, Daniel | 2007-04-14 | Complete
Bot 4 construction | Elwin | 2007-04-14 | On-going
Programming - preliminary | Group 1, Group 2, Group 3, Group 4 | 2007-04-14
Bot 1 code | Roger | 2007-04-14 | On-going | Fine-tuning
Bot 2 code | Brian, Ashish | 2007-04-14 | Not Started - Behind schedule | layout done
Bot 3 code | Stephen, Justin | 2007-04-14 | On-going | Fine-tuning
Bot 4 code | Elwin | 2007-04-14 | Not Started - Behind schedule
Integrating Bot 1 & Bot 3 | Group 1, Group 3 | 2007-04-14
mobility | Roger, Chris E, Chris H, Brian | 2007-04-14 | On-going | Testing and Fine-tuning
scoring | Ashish | 2007-04-14 | On-going - behind schedule | Testing
Integrating Bot 2 & Bot 3 | Group 2, Group 3 | 2007-04-14
mobility | Brian, Ashish, Stephen, Justin, Daniel | 2007-04-14 | Not Started - Behind schedule
scoring | Ashish | 2007-04-14 | Not Started - Behind schedule
Integrating Bot 2 & Bot 4 | Group 2, Group 4 | 2007-04-14
mobility | Brian, Ashish, Elwin | 2007-04-14 | Not Started - Behind schedule
scoring | Ashish | 2007-04-14 | Not Started - Behind schedule
Documentation | Chris Hogan, Chris Emr | 2007-04-14 | Complete
Week 5
Goals | Responsible | Milestone | Status | Notes
Evaluate Designs | Group 1, Group 2, Group 3 | 2007-04-18 | Complete | Bot 4 design (sorting the leaves and the pineapples) seems increasingly impossible; the design is dropped
Construction | Group 1, Group 2, Group 3 | 2007-04-21
Bot 1 construction | Roger, Chris E, Chris H, Eliot | 2007-04-21 | Complete
Bot 2 construction | Ashish | 2007-04-21 | On-going | servo malfunctions; design is more complicatedthan previously thought
Bot 3 construciton | Justin, Daniel | 2007-04-21 | Complete | Initial design complete
Bot 4 construction | Elwin | 2007-04-21 | On-going | Trying to find effective method of gathering leaves and pineapples
Programming - editing versions | Group 1, Group 2, Group 3, Group 4 | 2007-04-21
Bot 1 code | Roger | 2007-04-21 | On-going | always fine tuning
Bot 2 code | Brian, Ashish | 2007-04-21 | Not started | layout done
Bot 3 code | Stephen, Justin | 2007-04-21 | On-going | always fine tuning
Bot 4 code | Elwin | 2007-04-21 | Not started | far behind - will we really have to scrap this robot??
Integrating Bot 1 & Bot 3 | Group 1, Group 3 | 2007-04-21 |  | starting with the two already construted and programmed robots
mobility | Roger, Chris E, Chris H, Brian | 2007-04-21 | On-going | It all fits in the starting box
scoring | Stephen, Justin | 2007-04-21 | On-going | hi-score: 34 rockin' pts!
Integrating Bot 2 & Bot 3 | Group 2, Group 3 | 2007-04-21 |  | Bot 2 has problems with Bot 3
mobility | Brian, Ashish, Stephen, Justin, Daniel | 2007-04-21 | Not started
scoring | Ashish | 2007-04-21 | Not started
Documentation | Chris Emr, Chris Hogan, Brian Zhang, Justin Gura | 2007-04-21 | Complete
Week 6
Goals | Responsible | Milestone | Status | Notes
Evaluate Designs | Group 1, Group 2, Group 3 | 2007-04-25
Programming | Group 1, Group 2, Group 3 | 2007-04-28
Bot 1 code | Brian | 2007-04-28
Bot 2 code | Brian, Ashish | 2007-04-28
Bot 3 code | Stephen, Justin | 2007-04-28
Bot 4 code | Elwin | 2007-04-28
Integrating Bot 1 & Bot 2 | Group 1, Group 2 | 2007-04-28
mobility | Roger, Chris E, Chris H, Brian, Ashish | 2007-04-28
scoring | Ashish | 2007-04-28
Integrating Bot 2 & Bot 3 | Group 2, Group 3 | 2007-04-28
mobility | Brian, Ashish, Stephen, Justin, Daniel | 2007-04-28
scoring | Ashish | 2007-04-28
Testing |  | 2007-04-28
Bot 1 test |  | 2007-04-28
Bot 2 test |  | 2007-04-28
Bot 3 test |  | 2007-04-28
Documentation | Justin, Elwin, Brian | 2007-04-28
Week 7
Goals | Responsible | Milestone | Status | Notes
Evaluate Designs | Group 1, Group 2, Group 3 | 2007-05-01
Programming | Group 1, Group 2, Group 3 | 2007-05-05
Bot 1 code | Brian | 2007-05-05
Bot 2 code | Brian, Ashish | 2007-05-05
Bot 3 code | Stephen, Justin | 2007-05-05
Integrating Bot 1 & Bot 2 | Group 1, Group 2 | 2007-05-05
mobility | Roger, Chris E, Chris H, Brian, Ashish | 2007-05-05
scoring | Ashish | 2007-05-05
Integrating Bot 2 & Bot 3 | Group 2, Group 3 | 2007-05-05
mobility | Brian, Ashish, Stephen, Justin, Daniel | 2007-05-05
scoring | Ashish | 2007-05-05
Testing |  | 2007-05-05
Bot 1 test |  | 2007-05-05
Bot 2 test |  | 2007-05-05
Bot 3 test
Documentation | Justin, Elwin, Brian | 2007-05-05
Presentation | Justin, Elwin, Brian | 2007-05-12
Week 8
Goals | Responsible | Milestone | Status | Notes
Evaluate Designs | Group 1, Group 2, Group 3, Group 4 | 2007-05-03
Testing
Bot 1 test
Bot 2 test
Bot 3 test
Documentation | Justin, Elwin, Brian | 2007-05-05
Presentation | Justin, Elwin, Brian | 2007-05-12