## Sheet1
Explorer Post 1010 Botball Team 0129
Team Members: |  | Documentation: | Building: | Coding:
Kevin Heithaus | Terry Sifrit | Kevin Heithaus | Misha Shangold | Dana Reback
Misha Shangold | Brandon Nishan | Arleen Thukral | Stuart Brothers | Jay Koby
Arleen Thukral | David Wikman |  | David Wikman | Zachary Baer
Jay Koby | Zachary Baer |  | Misha Shangold | Alex Silvey
Stuart Brothers | Alex Silvey |  | Robert Chatterson
Robert Chatterson | Dana Reback |  | Terry Sifrit
| James Brent |  | James Brent
Milestones/Tasks | Assignment | Day | Status | Notes
Week 1:
Build Game Board | Bob Ekman, Sponsor | 2007-03-21 | Complete | Thanks Bob and Paul!
Learn Game Rules | All | 2007-03-19 | Complete | Interesting game this year.
Concept Ideas
Record concept ideas | Kevin, Arleen, Dana | 2007-03-19 | Complete
Botball Doc. site - assignment | Kevin | Through 07-Apr-07 | Complete
Project Plan | Kevin | 2007-03-31 | Complete
Brainstorming Ideas | All | 2007-03-19 | Complete | Lots of good ideas from all.
Week 2:
Documentation | Kevin, Arleen | 2007-03-28 | Complete
Construction
Bot 1 Building | David, Misha | 2007-03-28 | Incomplete, will continue
Bot 2 Building | Robert, Zach | 2007-03-31 | Design stage
Sensor Experimentation |  |  |  | Checking to make sure that sensors can pick up tribbles and houses
Sonar Testing | Jay, Brandon | 2007-03-28 | Complete
Camera Testing | Misha, Stuart | 2007-03-28 | Complete
Experimentation |  |  |  | Mostly with tribble sorting, still not sure if we can devote this many people to random concepts
Tribble Sorting | Terry, Dana | 28/31-Mar-07 | Incomplete, next week
Water Claw | Misha | 2007-03-31 | Complete
Week 3: |  |  |  | We made effective use of spring break by coming in and completing construction on both bots
Documentation | Kevin | 2007-04-04 | Complete
Construction
Bot 1 House Mechanism | David | 2007-04-02 | Complete
Bot 1 Chassis | Stuart | 2007-04-02 | Incomplete | Need this to be done to begin testing the house bot
Bot 2 Water Claw | Misha | 2007-04-04 | Complete | Will test on Friday for feasibility
Bot 2 Chassis | James | 2007-04-02 | Incomplete, will finish Weds
Coding
Simulation for Bot 1 | Dana
Sensor Testing | Jay | 2007-04-04 | Incomplete | Sonar is causing problems
Test code for Bot 2 | Alex | 2/4-Apr-07 | Complete | Will load code and test on Saturday
Team Progress Meeting | All | 2007-04-07 |  | Good ideas, reassessed the plans we originally made. Rejected some ideas, less experimentation
Week 4: |  |  |  | As we began to code, we faced difficulties with navigation with respect to getting House Mechanism Bot over the PVC pipe
Documentation | Kevin, Arleen | 2007-04-11 | Complete
Coding
Sensor Experimentation | Jay, Alex | 2007-04-11 | Incomplete | Hopefully we'll finally figure out our sonar problems
Bot 1 Coding | Zach | 2007-04-14 | Incomplete | Bot 1 is done, just testing mechanism
Bot 2 Coding | Dana | 2007-04-14 | Incomplete
Building
Bot 1 Chassis | Stuart | 2007-04-11 | Incomplete | When the chassis (for both bots) are finished, we can load up some code and get our sensor navigation down
Bot 2 Chassis | James | 2007-04-11 | Incomplete
Experimentation
Tribble Mechanism | Kevin, Terry | 2007-04-14 | Incomplete | On the 14th we will determine if we continue the testing
Team Progress Meeting | All | 2007-04-07 |  | Not everyone is able to participate in all the meetings because of other commitments (school plays, family events, homework)
Week 5:
Coding
Bot 1 Code | Stuart, | 2007-04-18 | Complete | We submtted the code design for documentation
Bot 2 Code | Dana, Jay | 2007-04-18 | Incomplete | We submtted the code design for documentation
Building
Refining Bot 1 | Misha | 2007-04-18 | Complete | We made minor modifications with detachable arm and sensory equipment.
Refining Bot 2 | David, James | 2007-04-18 | Complete
Update Project Plan | Kevin, Arleen | 2007-04-21 | Complete | Submitted
Experimentation
Test robot on gameboard | Terry | 2007-04-21 | Incomplete | Taking notes on what to change. We don't have any scoring data yet.
Team Progress Meeting | All | 2007-04-21 |  | As a result of trepidation for AP exams, we are facing difficulties with participation as many members could not find time to participate. Still we made progress this week.
Week 6:
Documentation | Kevin, Arleen, Dana | 2007-04-23 | In Progress, Will turn in. | The documentation is working fine now. With more people showing up, we can partition out jobs and get our work done more effeciently.
Testing
Bot 1 Testing | Misha, James | 2007-04-23 | Complete | Preliminary testing has been catastropic. Our robots have major, fundamental flaws that we did not see.
Bot 2 Testing | Stuart, Terry | 2007-04-23 | Incomplete, high priority. | This robot has not been tested yet, it's our top priority: finish building it.
Design Refinement | Build Team
Bot 1 Refinement |  | 2007-04-25 | Complete | The house robot was having problems with tribbles being caught in the wheels (as shown by our testing), meaning we needed to shield the wheels.
Bot 2 Refinement |  | 2007-04-25 | Complete | The testing for this robot is still going on. Preliminary results have shown that it's having issues with getting into the right position
Coding | Coding Team
Bot 1 Code Writing |  | 2007-04-25 | Still being refined. | Fixing some of the issues in our alpha versions of the code
Bot 2 Code Writing |  | 2007-04-25 | Incomplete | Have writtin preliminary code, but it is kind of difficult to write code for a robot that isn't done
Team Progress Meeting | All | 2007-04-28 |  | Our main problem this week has been starting to get our robots tested, and trying to make people show up to meetings.
Week 7:
Documentation | Kevin, Arleen, Dana | 2007-04-29 | In progress. | The documentation effort continues! We have started discussing the lesson's we've learned and how our robot has evolved.
Testing
Bot 1 Testing |  | 2007-04-29 | In progress. | Testing has been better; our percentages have been higher, since we've worked out our minor mechanical flaws.
Bot 2 Testing |  | 2007-04-29 |  | This robot has shown to be more reliable, after we have refined the code. Our arm operation is closer to desired.
Design Refinement | Build Team
Bot 1 Refinement |  | 2007-05-02 | Complete | The tribble shields have been attached to the robot, and it's running much smoother now.
Bot 2 Refinement |  | 2007-05-02 | Complete | Our mechanical issues have been worked out; the issues with the code is a whole new story.
Coding | Coding Team
Bot 1 Code Writing |  | 2007-05-02 | In progress, near done. | Our code for this robot is near perfect. We just need to modify so the two code so that it works with the other robot
Bot 2 Code Writing |  | 2007-05-02 | In progress. | This code still has minor tweaks to be made to it; our testing has shown success chances to be far below what we want
Team Progress Meeting | All | 2007-05-05 |  | Our progress is much greater than our projections, we will finish on time.
Week8:
Documentation | Kevin, Arleen, Dana | 2007-05-07 | Done | The documentation was finished and turned in on this day, or is in the process of being turned in tomorrow, after minor refinement tomorrow.
Testing
Bot 1 Testing | Misha, James | 2007-05-07 | In Progress | Testing has been ceased to concentrate on making the water robot work consistently.
Bot 2 Testing | Stuart, Terry | 2007-05-07 | In Progress | The water robot just needs some testing and debugging, to make it consistent. Mechanically, it is perfectly capable of scoring the 10 points it's required to, the code needs to reflect that.
Design Refinement | Building Team | 2007-05-09
Bot 1 Refinement |  |  | Complete | Both robots are pretty much mechanically done at this point. Just minor fixes are needed.
Bot 2 Refinement |  |  | Complete | See above.
Coding | Coding Team | 2007-05-09
Bot 1 Code Writing |  |  | In Progress | Generic testing and debugging processes are being executed on both robots, to make sure they work together consistently.
Bot 2 Code Writing |  |  | In Progress | See above
Tournament Presentation | Arleen, Kevin
Test and Refine All Bots/Code | All | 2007-05-11 |  | This is going to be an interesting day.
Note on A11: Milestones will be written in bold italics and tasks will have a regular font