## Sheet1
Date | Time | Place | Event/Topic | Hours | Team 129 | Team 130 | Labor
Saturday, March 17 | 8am-6pm | Maryland University | Workshop | 8 | 2 | 2 | 32
Sunday, March 18 | 8am-6pm | Maryland University | Workshop | 8 | 2 | 2 | 32
Monday, March 19 | 7-9pm | Lockheed Martin | Planning Session | 2 | 5 | 5 | 20
Wednesday, March 21 | 7-9pm | Lockheed Martin | Work Session | 2 |  |  | 0
Saturday, March 24 | 9am-noon | Lockheed Martin | Week 1 Status | 3 |  |  | 0
Wednesday, March 28 | 7-9pm | Lockheed Martin | Work Session | 2 |  |  | 0
Saturday, March 31 | 9am-noon | Lockheed Martin | Week 2 Status | 3 |  |  | 0
Monday, April 2 | 1-4pm | Lockheed Martin | Documentation 1 | 3 |  |  | 0
Wednesday, April 4 | 4-9pm | Lockheed Martin | Work Session | 5 |  |  | 0
Friday, April 6 | 1-4pm | Lockheed Martin | Work Session | 3 |  |  | 0
Saturday, April 7 | 9am-noon | Lockheed Martin | Week 3 Status | 3 |  |  | 0
Monday, April 8 | 1-4pm | Lockheed Martin | Work Session | 3 |  |  | 0
Wednesday, April 11 | 6-9pm | Lockheed Martin | Work Session | 3 |  |  | 0
Saturday, April 14 | 9am-noon | Lockheed Martin | Week 4 Status | 3 |  |  | 0
Wednesday, April 18 | 6-9pm | Lockheed Martin | Work Session | 3 |  |  | 0
Saturday, April 21 | 9am-noon | Lockheed Martin | Week 5 Status | 3 |  |  | 0
Monday, April 23 | 7-9pm | Lockheed Martin | Documentation 2 | 3 |  |  | 0
Wednesday, April 25 | 6-9pm | Lockheed Martin | Work Session | 3 |  |  | 0
Saturday, April 28 | 9am-noon | Lockheed Martin | Week 6 Status | 3 |  |  | 0
Sunday, April 29 | 11am-6pm | Montgomery College Rockville | Engineering Exhibit | 7 |  |  | 0
Wednesday, May 2 | 6-9pm | Lockheed Martin | Work Session | 3 |  |  | 0
Saturday, May 5 | 9am-noon | Lockheed Martin | Week 7 Status | 3 |  |  | 0
Monday, May 7 | 6-9pm | Lockheed Martin | Documentation Final | 3 |  |  | 0
Wednesday, May 9 | 6-9pm | Lockheed Martin | Work Session | 3 |  |  | 0
Friday, May 11 | 3-8pm | Lockheed Martin | Tournament Prep | 5 |  |  | 0
Saturday, May 12 | 7am-7pm | Maryland University | Tournament | 12 |  |  | 0
|  |  |  | 102 | 9 | 9 | 84