## Team 92
TEAM 92 2008 SCHEDULE
Adult Advisors: Bob Ekman, Paul Newell
Team members | Bot 1 | Bot 2 | Bot 3 | Bot 4
Alex O | Chris E * | Chris H * | (DISCONTINUED) | (DISCONTINUED)
Alex S | Alex O | Arvind H
Arvind H | John K | Katherine K
Austin G | Jeffrey | Austin G
Chris Emr | Katie D | Roger D
Chris Hogan | Alex S | Eliot RC
Eliot Rudnick-Cohen
Jeffrey G
John K
Katherine K
Katie D
Roger D
* (Doc) stands for Documentation; this person contributes raw information to the Documentation Lead
Week 1
Goals | Responsible | Milestone | Status | Notes
Build Game Board | Paul Newell | 2008-03-17 | Completed Ahead of Schedule | The board is a bit bigger that last year…
Learn Game Rules (watch promo video) | ALL | 2008-03-17 | Complete On Time | Great video this year!!
Inventory Kit | Roger, Chris E, Chris H, Eliot RC | 2008-03-19 | Complete On Time
Check FAQ | ALL | 2008-03-19 | Complete On Time | We were able to gain interesting ideas by reading the Frequently asked questions
Initial Designs | ALL | 2008-03-22 | Completed On Time
Documentation | Chris E, Chris H | 2008-03-22 | Completed On Time
Week 2
Goals | Responsible | Milestone | Status | Notes
Create Groups | Roger D | 2008-03-17 | Completed Ahead of Schedule
Study Game Board | ALL | 2008-03-22 | Completed On Time
Discuss Designs | ALL | 2008-03-24 | Completed On Time
Begin Models | ALL | 2008-03-24 | Completed On Time
Study Past Code | Eliot RC, Austin G | 2008-03-24 | Completed On Time | Teams can learn from last years success
Study Past Model | Katherine K, Alex O | 2008-03-24 | Completed On Time
Begin Construction | ALL | 2008-03-26 | Completed On Time
Gathering Materials | ALL
Bot 1 construction | Eliot RC, Alex S, John K | 2008-03-26 | In-progress
Bot 2 construction | Katie D, Arvind H, Alex O | 2008-03-26 | In-progress
Bot 3 construciton | Jeffery, Austin G | 2008-03-26 | In-progress | These two robots have become rejected ideas due to complications in design
Bot 4 construction | Roger D, Katherine K | 2008-03-26 | In-progress
Documentation | Chris E, Chris H | 2008-03-26 | In-progress
Week 3
Goals | Responsible | Milestone | Status | Notes
Study Past Code | Eliot RC, Austin G | 2008-03-29 | In-progress | Comparing last years codes and designs help us see if our current designs make sense
Study Past Model | Katherine K, Alex O | 2008-03-29 | In-progress
Evaluate Designs | Arvind H, Katie D | 2008-03-29 | In-progress
Construction - bases, arms, etc |  | 2008-04-02
Gathering Materials |  | 2008-04-02
Bot 1 construction |  | 2008-04-02
Bot 2 construction |  | 2008-04-02
Programming - start basic programming - movement
setup IC |  | 2008-04-02
Bot 1 code |  | 2008-04-05
Bot 2 code |  | 2008-04-05
Integrating Bot 1 & Bot 2 |  | 2008-04-05
mobility |  | 2008-04-05
scoring |  | 2008-04-05
Documentation | Chris E, Chris H | 2008-04-05
Week 4
Goals | Responsible | Milestone | Status | Notes
Evaluate Designs
Construction
Bot 1 construction
Bot 2 construction
Bot 3 construciton
Bot 4 construction
Programming
Bot 1 code
Bot 2 code
Bot 3 code
Bot 4 code
Integrating Bot 1 & Bot 2
mobility
scoring
Integrating Bot 2 & Bot 3
mobility
scoring
Integrating Bot 2 & Bot 4
mobility
scoring
Documentation | Chris E, Chris H
Week 5
Goals | Responsible | Milestone | Status | Notes
Evaluate Designs
Construction
Bot 1 construction
Bot 2 construction
Programming
Bot 1 code
Bot 2 code
Integrating Bot 1 & Bot 2
mobility
scoring
Documentation | Chris E, Chris H
Week 6
Goals | Responsible | Milestone | Status | Notes
Evaluate Designs
Programming
Bot 1 code
Bot 2 code
Integrating Bot 1 & Bot 2
mobility
scoring
Testing
Bot 1 test
Bot 2 test
Documentation | Chris E, Chris H
Week 7
Goals | Responsible | Milestone | Status | Notes
Evaluate Designs
Programming
Bot 1 code
Bot 2 code
Integrating Bot 1 & Bot 2
mobility
scoring
Testing
Bot 1 test
Bot 2 test
Documentation | Chris E, Chris H
Presentation | Chris E, Chris H