## Team 92
TEAM 92 2008 SCHEDULE
Adult Advisors: Bob Ekman, Paul Newell
Team members | Robot 1 (Urobot) | Robot 2 (Heisman) | Robot 3 | Robot 4
Alex O | Chris E * | Chris H * | (DISCONTINUED) | (DISCONTINUED)
Alex S | Alex O | Arvind H
Arvind H | John K | Katherine K
Austin G | Jeffrey | Austin G
Chris Emr | Katie D | Roger D*
Chris Hogan | Alex S | Eliot RC*
Eliot Rudnick-Cohen | Austin S*
Jeffrey G
John K
Katherine K
Katie D
Austin S
Roger D
* (Doc) stands for Documentation; this person contributes raw information to the Documentation Lead
Week 1
Goals | Responsible | Milestone | Status | Notes
Build Game Board | Paul Newell | 2008-03-17 | Completed Ahead of Schedule | The board is a bit bigger that last year…
Learn Game Rules (watch promo video) | ALL | 2008-03-17 | Complete On Time | Great video this year!!
Inventory Kit | Roger, Chris E, Chris H, Eliot RC | 2008-03-19 | Complete On Time
Check FAQ | ALL | 2008-03-19 | Complete On Time | We were able to gain interesting ideas by reading the Frequently asked questions
Initial Designs | ALL | 2008-03-22 | Completed On Time
Documentation | Chris E, Chris H | 2008-03-22 | Completed On Time
Week 2
Goals | Responsible | Milestone | Status | Notes
Create Groups | Roger D | 2008-03-17 | Completed Ahead of Schedule
Study Game Board | ALL | 2008-03-22 | Completed On Time
Discuss Designs | ALL | 2008-03-24 | Completed On Time
Begin Models | ALL | 2008-03-24 | Completed On Time
Study Past Code | Eliot RC, Austin G | 2008-03-24 | Completed On Time | Our team can learn from last years success
Study Past Model | Katherine K, Alex O | 2008-03-24 | Completed On Time
Begin Construction | ALL | 2008-03-26 | Completed On Time
Gathering Materials | ALL
Robot 1 construction | Eliot RC, Alex S, John K | 2008-03-26 | Completed On Time
Robot 2 construction | Katie D, Arvind H, Alex O | 2008-03-26 | Completed On Time
Robot 3 construciton | Jeffery, Austin G | 2008-03-26 | Completed On Time | These two robots have become rejected ideas due to complications in design
Robot 4 construction | Roger D, Katherine K | 2008-03-26 | Completed On Time
Documentation | Chris E, Chris H | 2008-03-26 | Completed On Time
Week 3
Goals | Responsible | Milestone | Status | Notes
Study Past Code | Eliot RC, Austin G | 2008-03-29 | Completed On Time | Comparing last years codes and designs help us see if our current designs make sense
Study Past Model | Katherine K, Alex O | 2008-03-29 | Completed On Time
Evaluate Designs | Arvind H, Katie D | 2008-03-29 | Completed On Time
Construction - bases, arms, etc | Roger D, Austin S, John K | 2008-04-02 | Completed On Time
Gathering Materials | All | 2008-04-02 | Completed On Time
Robot 1 construction | John K, Austin S | 2008-04-02 | Completed On Time | These are very simple early prototypes. Testing of these ideas will commence soon to evalutate these ideas
Robot 2 construction | Roger D, Eliot RC | 2008-04-02 | Completed On Time
Programming - start basic programming - movement |  |  | Completed On Time
setup IC | Roger D | 2008-04-02 | Completed On Time
Robot 1 code | Jeffrey, Alex S | 2008-04-05 | Completed On Time
Robot 2 code | Chris H, Austin G | 2008-04-05 | Completed On Time
Integrating Robot 1 & Robot 2 |  |  | Completed On Time | Code alteration must be made to allow robots to pass and complete all their desired tasks
mobility | Arvind H, Katie D | 2008-04-05 | Completed On Time
scoring | Alex O, Katherine K | 2008-04-05 | Completed On Time
Documentation | Chris E, Chris H, Austin S | 2008-04-05 | Completed On Time | Several of the FAQ's submitted by other teams helped our team's progress
Week 4
Goals | Responsible | Milestone | Status | Notes
Evaluate Designs | ALL | 2008-04-09 | In-progress | Talking with mentors helps quite a bit in this field
Construction
Robot 1 construction | Austin S, Jeffrey | 2008-04-09 | Completed On Time
Robot 2 construction | Eliot RC, Katherine K | 2008-04-09 | Completed On Time
Programming |  |  |  | We have completed much in the field of programming and testing this week, but testing is one thing that is never truly complete.
Robot 1 code | Roger D, Jeffrey | 2008-04-09 | In-progress
Robot 2 code | Eliot RC, Chris H | 2008-04-09 | In-progress
Testing
Robot 1 | Chris E, John K | 2008-04-12 | In-progress
Robot 2 | Austin G, Katie D | 2008-04-12 | In-progress
Integrating Robot 1 & Robot 2 |  |  |  | It would help if our robots did not run into each other…
mobility | Arvind H, Katie D | 2008-04-12 | In-progress
scoring | Alex O, Katherine K | 2008-04-12 | Completed On Time
Documentation | Chris E, Roger D, Eliot RC | 2008-04-14 | Completed ahead of schedule
Week 5
Goals | Responsible | Milestone | Status | Notes
Evaluate Designs |  | 2008-04-16
Construction
Robot 1 construction |  | 2008-04-16
Robot 2 construction |  | 2008-04-16
Programming
Robot 1 code |  | 2008-04-16
Robot 2 code |  | 2008-04-16
Testing
Robot 1 test |  | 2008-04-19
Robot 2 test |  | 2008-04-19
Integrating Robot 1 & Robot 2
mobility |  | 2008-04-19
scoring |  | 2008-04-19
Documentation | Chris E, Chris H | 2009-04-28
Week 6
Goals | Responsible | Milestone | Status | Notes
Evaluate Designs |  | 2008-04-23
Programming
Robot 1 code |  | 2008-04-23
Robot 2 code |  | 2008-04-23
Integrating Robot 1 & Robot 2
mobility |  | 2008-04-23
scoring |  | 2008-04-23
Testing
Robot 1 test |  | 2008-04-23
Robot 2 test |  | 2008-04-23
Documentation | Chris E, Chris H | 2008-04-28
Week 7
Goals | Responsible | Milestone | Status | Notes
Evaluate Designs |  | 2008-04-26
Programming
Robot 1 code |  | 2008-04-26
Robot 2 code |  | 2008-04-26
Integrating Robot 1 & Robot 2
mobility |  | 2008-04-26
scoring |  | 2008-04-26
Testing
Robot 1 test |  | 2008-04-30
Robot 2 test |  | 2008-04-30
Documentation | Chris E, Chris H | 2008-04-28
Presentation | Chris E, Chris H | 2008-05-02