## Sheet1
TEAM 93 2008 SCHEDULE
Adult Advisors: Bob Ekman
Team members | Bot 1 (XBC) | Bot 2 (Create) | Docunmentation
Stephen C | Justin G * | Stephen C * | Kevin H (Lead)
Adam B | Adam F | Tyler S | Stephen C
Adam F | Darpan K | Zeshan T | Adam B
Justin G | Megan H | Brian B
Ben W | Sehroze K | Ben W
Brian B | David | Kevin H
Darpan K
Kevin H
Megan H
Shehroze K
Tyler S
Zeshan T
* (Doc) stands for Documentation; this person contributes raw information to the Documentation Lead
Week 1
Goals | Responsible | Milestone | Status | Notes
Build Game Board | ALL | 2008-03-17 | In progress | Almost done, still need to lay down some markings.
Learn Game Rules (watch promo video) | ALL | 2008-03-17 | Complete | Bridges? The board is almost three times as big as last year.
Inventory Kit | Brian, Darpan | 2008-03-19 | Complete | Thought we lost some allen wrenches, they were in the bottom of the box
Check FAQ | Stephen | 2008-03-19 | On-going | If we have any more rules questions, we wil ask.
Initial Designs | ALL | 2008-03-19 | Completed | We have some great ideas, we're getting ready to implement them.
Week 2
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-03-26 | Complete | We're moving ahead of schedule; we're already on the board and testing
Begin Models | Adam F, Ben W | 2008-03-26 | In progress | We're still familiarizing ourselves with CAD programs
Study Past Code | Justin, Stephen | 2008-03-28 | Complete | We can re-use some of the movement methods from last year.
Study Past Model | Brian, Darpan | 2008-03-28 | In progress | We need to familiarize ourselves with CAD Modeling
Begin Construction | Bot 1, Bot 2 | 2008-03-26 | On-going | We're ahead of schedule; we started building on March 19th
Gathering Materials | Megan, Tyler | 2008-03-26 | Complete | Can't build without materials
Bot 1 construction | Group 1 | 2008-03-31 | In progress | Challenge: getting the robot small enough to get over the bridge
Bot 2 construction | Group 2 | 2008-03-31 | In progress | Challenge: finding space for our mechanical features (arms and manipulators) on the Create
Documentation | Kevin, Stephen | 24 to 29-Mar-08 | On-going
Week 3
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-04-02 | Complete | Our progress is going well, so we're going to slow down and try some additional ideas and see if they work better
Construction
Bot 1 construction | Adam, Darpan, Sehroze | 2008-04-02 | Complete | We're largely complete with this robot, maybe tweaking one thing or another
Bot 2 construction | Tyler, Brian, Ben | 2008-04-02 | In Progress | We're tossing around some ideas that might make this robot work better mechanically, like a turret
Programming
setup IC | Stephen | 2008-04-05 | Complete | We somehow lost all the memory on a laptop, so we had to reload all of the botall software
Bot 1 code | Justin, Megan | 2008-04-05 | In Progress | This code is working well; we only need to make minor modifications to it and make it work better.
Bot 2 code | Stephen, Kevin | 2008-04-05 | In Progress | We're running two different programs; one using the bulldozer, the other without it. We're going to run more tests to see which one does better
Testing |  |  |  | We are way ahead of schedule on building, so we should allocate time to test earlier than past years.
Bot 1 Testing |  | 2008-04-05 | On-going | The robot is getting over the bridge more consistently
Bot 2 testing | Stephen | 2008-04-05 | On-going | We're working out the exact movements needed to sort the tribbles with our claw.
Documentation | Kevin | 2008-04-05 | On-going | We did pretty good on the documentation, but we're trying to figure out how to score higher than a 4
Week 4
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-04-09 | Complete | We're moving very quickly, moreso than last year. More time to test
Construction
Bot 1 construction | Adam, Darpan, Sehroze | 2008-04-09 | Complete | We're making minor tweaks to the design to improve on it's consistency
Bot 2 construction | Tyler, Brian, Ben | 2008-04-09 | In-progress | We're still testing and figuring out the best way to score points with tribbles, and if we want to use some other ideas
Programming
Bot 1 code | Justin, Megan | 2008-04-12 | In-progress | Both codes are being constantly tested and tweaked.
Bot 2 code | Stephen, Ben | 2008-04-12 | In-progress | We are attempting to work out the movements for sorting tribbles
Integrating Bot 1 & Bot 2 |  |  |  | The bots have to work together
mobility | Adam, Darpan, Megan | 2008-04-12 | In-progress | Bot 1 still needs to disrupt the other team on the other side of the board.
scoring | Stpehen, Ben, Tyler | 2008-04-12 | In-progress | We're refining Bot 1 to sweep the umbrellas better
Documentation | Kevin, Stephen | 9 to 12-Apr-08 | On-going | We got all of the documentation in on time.
Week 5
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-04-16 | Complete | We're waiting with bated breath for the documentation scores
Construction |  |  |  | We want to be completely done building at this point
Bot 1 construction | Adam, Darpan, Sehroze | 2008-04-16 | Complete | There are no more changes to be made with this robot; now we just need to tweak the code for both seeding and elimination
Bot 2 construction | Tyler, Brian, Ben | 2008-04-16 | Behind schedule (we wanted to be done building) | We threw out the idea of putting our claw on a turret, sticking with our initial design.
Programming
Bot 1 code | Justin, Megan | 2008-04-19 | In-progress | We need to branch out and work on the seeding round code
Bot 2 code | Stephen, Ben | 2008-04-19 | In-progress | We have the tribble sorting almost completely figured out; we need to incorporate the cups into our plan and work on scoring more points
Integrating Bot 1 & Bot 2
mobility | Adam, Darpan, Megan | 2008-04-19 | In-progress | We've run the bots together a few times and they don't interfere with each other.
scoring | Stpehen, Ben, Tyler | 2008-04-19 | In-progress | We need to incorporate some scoring on the other side of the board for the seeding roung
Documentation | Kevin, Stephen | 16 to 19-Apr-08 | On-going
Week 6
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-04-23 | Complete | We're entering the final two weeks; our progress is good and we're hoping to be done in time.
Construction
Bot 2 construction | Stephen, Darpan, Brian | 2008-04-23 | Complete | We finished all of the construction on this robot only a meeting behind schedule.
Programming
Bot 1 code | Justin, Megan | 2008-04-23 | In-progress | We're refining our offensive tacticts in elmination and our additional points in seeding
Bot 2 code | Stephen, Ben | 2008-04-23 | In-progress | We're working on scoring points with the cups
Integrating Bot 1 & Bot 2
mobility | Adam, Darpan, Megan | 2008-04-26 | Complete | The robots run together well; since they are on opposite sides of the board most of the time, there are few problems to encounter here
scoring | Stpehen, Ben, Tyler | 2008-04-26 | In-progress | Bot 2's scoring is vital, as it provides most of our points.
Testing
Bot 1 test | Adam, Darpan, Sehroze | 2008-04-26 | On-going | It's much more consistent in getting to the other side of the board now.
Bot 2 test | Tyler, Brian, Ben | 2008-04-26 | On-going | We had to test on a smaller board this time; the PVC was not attached to the board, so it kept moving and we did not do as well as hoped
Documentation | Kevin, Stephen | 2008-04-26 | On-going | We wished for better scores this time around; we will pay much closer attention to the requirements this time
Week 7
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-04-28 | Complete | Final week; we're just continuing to test and refine and get major consistency.
Programming
Bot 1 code | Justin, Megan | 2008-04-28 | Complete | We’re done with the code a meeting or two early; no late nights before regionals this year!
Bot 2 code | Stephen, Tyler S | 2008-04-28 | Complete | This code is done as well. The 28th was a very good meeting.
Integrating Bot 1 & Bot 2
scoring | Stpehen, Ben, Tyler | 2008-04-30 | Complete | The two robots are scoring as much as they can.
Testing
Bot 1 test | Adam, Darpan, Sehroze | 2008-05-02 | Complete | No major changes today, right before the tournament. Everything looks good.
Bot 2 test | Tyler, Brian, Ben | 2008-05-02 | Complete | Same as above.
Documentation | Kevin, Stephen | 2008-04-28 | Complete | We enjoyed ourselves taking the glamour shot!