## Sheet1
TEAM 196 2008 SCHEDULE
Adult Advisors: Bob Ekman
Team members | Bot 1 (XBC) | Bot 2 (Create) | Documentation | Notes
Andrew B | Terry S * | Elwin W * | Dana R | This year's team is great!
Arleen T | Andrew B | Samir S | Arleen T
Dana R | Eric A | James M
Elwin W | Richard A | Ermias K
Eric A | Julia C | Nicholas A
Ermias K | Misha S | Seth R
James M
Julia C
Misha S
Nicholas A
Richard A
Samir S
Seth R
Terry S
* (Doc) stands for Documentation; this person contributes raw information to the Documentation Lead
Week 1
Goals | Responsible | Milestone | Status | Notes
Build Game Board | ALL | 2008-03-17 | Complete | Completed and fully functional!
Learn Game Rules (watch promo video) | ALL | 2008-03-17 | Complete | Potential challenges include the bridges, pom sorting, and grabbing Botguy/the Garden.
Inventory Kit | Terry, Julia | 2008-03-19 | Complete | All parts accounted for.
Check FAQ | Arleen | 2008-03-19 | On-going | If we have any more rules questions, we will ask them.
Initial Designs | ALL | 2008-03-19 | Complete | We came up with many good ideas, rejected a few, and we believe that our current designs will be easy to implement and successful.
Week 2
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-03-26
Begin Models | Julia, Seth | 2008-03-26 | Complete | Begun work on models.
Study Past Code | Andrew, Nicholas | 2008-03-28 | Complete | We can slightly improve some of last years methods for more accurate movement.
Study Past Model | Brian, Darpan | 2008-03-28 | In progress | We need to familiarize ourselves with CAD Modeling.
Begin Construction | Bot 1 team, Bot 2 team | 2008-03-26 | On-going | We are ahead of schedule, we started building Mar 19. Progress made on both bots, although we have had some technical difficulties.
Gathering Materials | Eric, Samir | 2008-03-26 | Complete | Can't build without the proper materials!
Bot 1 construction | Bot 1 team | 2008-03-31 | In progress | Challenge: getting the robot to balance with its long attachment.
Bot 2 construction | Bot 2 team | 2008-03-31 | In progress | Challenge: making the arms on the create sturdy enough/compact enough to fit within the size limits.
Documentation | Dana, Arleen | 24 to 29-Mar-08 | On-going | We're hard at work!
Week 3
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-04-02
Construction
Bot 1 construction | Terry, Eric, Richard | 2008-04-02
Bot 2 construction | Elwin, Samir, James | 2008-04-02
Programming
setup IC | Julia, Ermias | 2008-04-05
Bot 1 code | Andrew, Misha | 2008-04-05
Bot 2 code | Nicholas, Seth | 2008-04-05
Documentation | Dana, Arleen | 2008-04-05
Week 4
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-04-09
Construction
Bot 1 construction | Terry, Eric, Richard | 2008-04-09
Bot 2 construction | Elwin, Samir, James | 2008-04-09
Programming
Bot 1 code | Andrew, Misha | 2008-04-12
Bot 2 code | Nicholas, Seth | 2008-04-12
Integrating Bot 1 & Bot 2
mobility | Julia, Andrew, Terry | 2008-04-12
scoring | Ermias, Dana, Elwin | 2008-04-12
Documentation | Dana, Arleen | 9 to 12-Apr-08
Week 5
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-04-16
Construction |  |  |  | We want to be completely done building at this point.
Bot 1 construction | Terry, Eric, Richard | 2008-04-16
Bot 2 construction | Elwin, Samir, James | 2008-04-16
Programming
Bot 1 code | Andrew, Misha | 2008-04-19
Bot 2 code | Nicholas, Seth | 2008-04-19
Integrating Bot 1 & Bot 2
mobility | Julia, Andrew, Terry | 2008-04-19
scoring | Ermias, Dana, Elwin | 2008-04-19
Documentation | Dana, Arleen | 16 to 19-Apr-08
Week 6
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-04-23
Programming
Bot 1 code | Terry, Eric, Richard | 2008-04-23
Bot 2 code | Elwin, Samir, James | 2008-04-23
Integrating Bot 1 & Bot 2
mobility | Andrew, Misha | 2008-04-26
scoring | Nicholas, Seth | 2008-04-26
Testing
Bot 1 test | Julia, Andrew, Terry | 2008-04-26
Bot 2 test | Ermias, Dana, Elwin | 2008-04-26
Documentation | Dana, Arleen | 2008-04-26
Week 7
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-04-28
Programming
Bot 1 code | Terry, Eric, Richard | 2008-04-28
Bot 2 code | Elwin, Samir, James | 2008-04-28
Integrating Bot 1 & Bot 2
mobility | Andrew, Misha | 2008-04-30
scoring | Nicholas, Seth | 2008-04-30
Testing
Bot 1 test | Julia, Andrew, Terry | 2008-05-02
Bot 2 test | Ermias, Dana, Elwin | 2008-05-02
Documentation | Dana, Arleen | 2008-04-28