## Sheet1
TEAM 196 2008 SCHEDULE
Adult Advisors: Bob Ekman
Team members | Bot 1 (XBC) | Bot 2 (Create) | Documentation | Notes
Andrew B | Terry S * | Elwin W * | Dana R | This year's team is great!
Arleen T | Andrew B | Samir S | Arleen T
Dana R | Eric A | James M
Elwin W | Richard A | Ermias K
Eric A | Julia C | Nicholas A
Ermias K | Misha S | Seth R
James M
Julia C
Misha S
Nicholas A
Richard A
Samir S
Seth R
Terry S
* (Doc) stands for Documentation; this person contributes raw information to the Documentation Lead
Week 1
Goals | Responsible | Milestone | Status | Notes
Build Game Board | ALL | 2008-03-17 | Complete | Completed and fully functional!
Learn Game Rules (watch promo video) | ALL | 2008-03-17 | Complete | Potential challenges include the bridges, pom sorting, and grabbing Botguy/the Garden.
Inventory Kit | Terry, Julia | 2008-03-19 | Complete | All parts accounted for.
Check FAQ | Arleen | 2008-03-19 | On-going | If we have any more rules questions, we will ask them.
Initial Designs | ALL | 2008-03-19 | Complete | We came up with many good ideas, rejected a few, and we believe that our current designs will be easy to implement and successful.
Week 2
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-03-26
Begin Models | Julia, Seth | 2008-03-26 | Complete | Begun work on models.
Study Past Code | Andrew, Nicholas | 2008-03-28 | Complete | We can slightly improve some of last years methods for more accurate movement.
Study Past Model | Brian, Darpan | 2008-03-28 | In progress | We need to familiarize ourselves with CAD Modeling.
Begin Construction | Bot 1 team, Bot 2 team | 2008-03-26 | On-going | We are ahead of schedule, we started building Mar 19. Progress made on both bots, although we have had some technical difficulties.
Gathering Materials | Eric, Samir | 2008-03-26 | Complete | Can't build without the proper materials!
Bot 1 construction (XBC) | Bot 1 team | 2008-03-31 | In progress | Challenge: getting the robot to balance with its long attachment.
Bot 2 construction (Create) | Bot 2 team | 2008-03-31 | In progress | Challenge: making the arms on the create sturdy enough/compact enough to fit within the size limits.
Documentation | Dana, Arleen | 24 to 29-Mar-08 | On-going | We're hard at work!
Week 3
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-04-02 | On-going | Currently evaluating mechanisms of Bot 2 for bridge bloker, sorting tribble trees, camera roaming on individual tribbles
Construction |  |  | On-going
Bot 1 construction (XBC) | Terry, Eric, Richard | 2008-04-02 |  | Working on the base to make the entire bot more stable in order to cross the ramp with greater efficiency. Also working on light sensor.
Bot 2 construction (Create) | Elwin, Samir, James | 2008-04-02 | Complete (now testing)
Programming
setup IC | Julia, Ermias | 2008-04-05 | Complete
Bot 1 code | Andrew, Misha | 2008-04-05 | Partially accomplished | Program for crossing the bridge pending
Bot 2 code | Nicholas, Seth | 2008-04-05 | Mainly Complete | Finished program for sorting two trees and route to solarium
Documentation | Dana, Arleen | 2008-04-05 | On-going | We learned that we do not have the updated model of the SolidWorks software (The older version has expired for education use). Hence we have to be creative with our use of pictures and formating. The primary focus remains on the construction modifications for improvement of scores and programming.
Week 4
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-04-09 | on-going
Construction |  |  | complete
Bot 1 construction (XBC) | Terry, Eric, Richard | 2008-04-09 | complete | The width of the bot has been reduced in order to efficiently cross the bridge.
Bot 2 construction (Create) | Elwin, Samir, James | 2008-04-09 | complete
Programming
Bot 1 code (XBC) | Andrew, Misha | 2008-04-12 | complete | This code accomplishes the task of getting the bot to the opponents side.
Bot 2 code (Create) | Nicholas, Seth | 2008-04-12 | complete | The code accomplishes many of the important scoring actions such as picking up cups with the arm, protecting the tribbles with the pen, and operating the tribble sorter and the bridgeblocker.
Integrating Bot 1 & Bot 2
mobility | Julia, Andrew, Terry | 2008-04-12 | on-going
scoring | Ermias, Dana, Elwin | 2008-04-12 | on-going | As most of the programming has just recently been completed, testing and programming are done simultaneously.
Documentation | Dana, Arleen | 9 to 12-Apr-08 | on-going | We are coping well with the vast amount of work to be completed and all member are very good workign together when we have unscheduled meetings to finish any uncompleted work.
Week 5
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-04-16
Construction |  |  |  | We want to be completely done building at this point.
Bot 1 construction (XBC) | Terry, Eric, Richard | 2008-04-16
Bot 2 construction (Create) | Elwin, Samir, James | 2008-04-16
Programming
Bot 1 code | Andrew, Misha | 2008-04-19
Bot 2 code | Nicholas, Seth | 2008-04-19
Integrating Bot 1 & Bot 2
mobility | Julia, Andrew, Terry | 2008-04-19
scoring | Ermias, Dana, Elwin | 2008-04-19
Documentation | Dana, Arleen | 16 to 19-Apr-08
Week 6
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-04-23
Programming
Bot 1 code | Terry, Eric, Richard | 2008-04-23
Bot 2 code | Elwin, Samir, James | 2008-04-23
Integrating Bot 1 & Bot 2
mobility | Andrew, Misha | 2008-04-26
scoring | Nicholas, Seth | 2008-04-26
Testing
Bot 1 test | Julia, Andrew, Terry | 2008-04-26
Bot 2 test | Ermias, Dana, Elwin | 2008-04-26
Documentation | Dana, Arleen | 2008-04-26
Week 7
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-04-28
Programming
Bot 1 code (XBC) | Terry, Eric, Richard | 2008-04-28
Bot 2 code (Create) | Elwin, Samir, James | 2008-04-28
Integrating Bot 1 & Bot 2
mobility | Andrew, Misha | 2008-04-30
scoring | Nicholas, Seth | 2008-04-30
Testing
Bot 1 test | Julia, Andrew, Terry | 2008-05-02
Bot 2 test | Ermias, Dana, Elwin | 2008-05-02
Documentation | Dana, Arleen | 2008-04-28