## Sheet1
TEAM 196 2008 SCHEDULE
Adult Advisors: Bob Ekman
Team members | Bot 1 (XBC) | Bot 2 (Create) | Documentation | Notes
Andrew B | Terry S * | Elwin W * | Dana R | This year's team is great!
Arleen T | Andrew B | Samir S | Arleen T
Dana R | Eric A | James M
Elwin W | Richard A | Ermias K
Eric A | Julia C | Nicholas A
Ermias K | Misha S | Seth R
James M
Julia C
Misha S
Nicholas A
Richard A
Samir S
Seth R
Terry S
* (Doc) stands for Documentation; this person contributes raw information to the Documentation Lead
Week 1
Goals | Responsible | Milestone | Status | Notes
Build Game Board | ALL | 2008-03-17 | Complete | Completed and fully functional!
Learn Game Rules (watch promo video) | ALL | 2008-03-17 | Complete | Potential challenges include the bridges, pom sorting, and grabbing Botguy/the Garden.
Inventory Kit | Terry, Julia | 2008-03-19 | Complete | All parts accounted for.
Check FAQ | Arleen | 2008-03-19 | On-going | If we have any more rules questions, we will ask them.
Initial Designs | ALL | 2008-03-19 | Complete | We came up with many good ideas, rejected a few, and we believe that our current designs will be easy to implement and successful.
Week 2
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-03-26
Begin Models | Julia, Seth | 2008-03-26 | Complete | Begun work on models.
Study Past Code | Andrew, Nicholas | 2008-03-28 | Complete | We can slightly improve some of last years methods for more accurate movement.
Study Past Model | Brian, Darpan | 2008-03-28 | In progress | We need to familiarize ourselves with CAD Modeling.
Begin Construction | Bot 1 team, Bot 2 team | 2008-03-26 | On-going | We are ahead of schedule, we started building Mar 19. Progress made on both bots, although we have had some technical difficulties.
Gathering Materials | Eric, Samir | 2008-03-26 | Complete | Can't build without the proper materials!
Bot 1 construction (XBC) | Bot 1 team | 2008-03-31 | In progress | Challenge: getting the robot to balance with its long attachment.
Bot 2 construction (Create) | Bot 2 team | 2008-03-31 | In progress | Challenge: making the arms on the create sturdy enough/compact enough to fit within the size limits.
Documentation | Dana, Arleen | 24 to 29-Mar-08 | On-going | We're hard at work!
Week 3
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-04-02 | On-going | Currently evaluating mechanisms of Bot 2 for bridge blocker, sorting tribble trees, camera roaming on individual tribbles
Construction |  |  | On-going
Bot 1 construction (XBC) | Terry, Eric, Richard | 2008-04-02 |  | Working on the base to make the entire bot more stable in order to cross the ramp with greater efficiency. Also working on light sensor.
Bot 2 construction (Create) | Elwin, Samir, James | 2008-04-02 | Complete (now testing)
Programming
Setup IC | Julia, Ermias | 2008-04-05 | Complete
Bot 1 code | Andrew, Misha | 2008-04-05 | Partially accomplished | Program for crossing the bridge pending.
Bot 2 code | Nicholas, Seth | 2008-04-05 | Mainly Complete | Finished program for sorting two trees and route to solarium.
Documentation | Dana, Arleen | 2008-04-05 | On-going | We learned that we do not have the updated model of the SolidWorks software (The older version has expired for education use). Hence we have to be creative with our use of pictures and formating. The primary focus remains on the construction modifications for improvement of scores and programming.
Week 4
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-04-09 | On-going
Construction |  |  | Complete
Bot 1 construction (XBC) | Terry, Eric, Richard | 2008-04-09 | Complete | The width of the bot has been reduced in order to efficiently cross the bridge.
Bot 2 construction (Create) | Elwin, Samir, James | 2008-04-09 | Complete | The attachment is slightly unstable, but constuction on it is complete.
Programming
Bot 1 code (XBC) | Andrew, Misha | 2008-04-12 | Complete | This code accomplishes the task of getting the bot to the opponents side.
Bot 2 code (Create) | Nicholas, Seth | 2008-04-12 | Complete | The code accomplishes many of the important scoring actions such as picking up cups with the arm, protecting the tribbles with the pen, and operating the tribble sorter and the bridgeblocker.
Integrating Bot 1 & Bot 2
Mobility | Julia, Andrew, Terry | 2008-04-12 | On-going
Scoring | Ermias, Dana, Elwin | 2008-04-12 | On-going | As most of the programming has just recently been completed, testing and programming are done simultaneously.
Documentation | Dana, Arleen | 9 to 12-Apr-08 | On-going | We are coping well with the vast amount of work to be completed and all members are very good working together when we have unscheduled meetings to finish any uncompleted work.
Week 5
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-04-16 | On-going | Checking the reliablility of our programs and designs.
Construction |  |  | Complete | Both the XBC and the iRobot Create were completed the previous week. Some minor changes have been made, but we are confident in out current designs.
Bot 1 construction (XBC) | Terry, Eric, Richard | 2008-04-16 | Complete | See above. We changed the placement of the wheels to increase mobility.
Bot 2 construction (Create) | Elwin, Samir, James | 2008-04-16 | Complete | See above. We modified the arm attachment to make it more stable, but otherwise there were no major changes.
Programming
Bot 1 code | Andrew, Misha | 2008-04-19 | Complete | Found a new way to make the turns more accurate and modified the code slightly; no major changes.
Bot 2 code | Nicholas, Seth | 2008-04-19 | Complete | Modified the turns slightly, otherwise, no major changes.
Integrating Bot 1 & Bot 2
Mobility | Julia, Andrew, Terry | 2008-04-19 | On-going | Took down observations on the mobility of our robot; everythign seems to be going well so far.
Scoring | Ermias, Dana, Elwin | 2008-04-19 | On-going | We have begun taking down scores for each trial that we do and using this information to figure out the circumstances under which our robot scores well and what changes need to be made.
Documentation | Dana, Arleen | 2008-04-19 | On-going | We got a head start on several areas of documentation this week, and are working with the programmers regarding documentation of source code.
Week 6
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-04-23 | On-going | Currently evaluating the accuracy of our programs and their consistency in scoring points.
Programming
Bot 1 code | Andrew, Misha | 2008-04-23 | Complete | Have made minor modifications in response to feedback from testing.
Bot 2 code | Nicholas, Seth | 2008-04-23 | Complete | Have made minor modifications in response to feedback from testing.
Integrating Bot 1 & Bot 2
Mobility | Julia, Andrew, Terry | 2008-04-26 | On-going | Found that avoiding poms was an issue; discussed with programmers and managed to resolve it.
Scoring | Ermias, Dana, Elwin | 2008-04-26 | On-going | Have noticed increased consistency in our scoring.
Testing
Bot 1 test | Terry, Richard, Elwin | 2008-04-26 | On-going | The XBC sometimes has difficulty getting onto the bridge; we found that this was an issue of positioning and resolved it.
Bot 2 test | Eric, Julia, Andrew | 2008-04-26 | On-going | We noticed some difficulty in scoring all poms; have decided to work with programmers on this issue.
Documentation | Dana, Arleen | 2008-04-26 | On-going | We have begun planning our presentation for competition day and finishing up our written documentation.
Week 7
Goals | Responsible | Milestone | Status | Notes
Evaluate Progress | ALL | 2008-04-28 | COMPLETE! | We feel that we have reliable robots and are ready for the regional competition.
Programming
Bot 1 code (XBC) | Andrew, Misha | 2008-04-28 | Complete | Programming for the XBC has been error-checked and is complete.
Bot 2 code (Create) | Nicholas, Seth | 2008-04-28 | Complete | Programming for the Create was modified slightly to improve accuracy and is now complete.
Integrating Bot 1 & Bot 2
mobility | Julia, Andrew, Terry | 2008-04-30 | Complete | Both bots are fully integrated with regard to mobility.
scoring | Ermias, Dana, Elwin | 2008-04-30 | Complete | Both bots are fully integrated with regard to scoring.
Testing
Bot 1 test | Terry, Richard, Elwin | 2008-05-02 | Complete | Our tests have shown that the XBC bot has no trouble getting across the bridge and into the other team's starting box: Bot 1 is ready for the competition.
Bot 2 test | Eric, Julia, Andrew | 2008-05-02 | Complete | We have noticed increased accuracy in scoring all poms and eliminating cups from the board: Bot 2 is ready for the competition.
Documentation | Dana, Arleen | 2008-04-28 | Complete | We are still rehearsing our presentation, but all of the written work is done. Ready for competition day!