## Sheet1
Date | Time | Place | Event/Topic | Hours | Team 92 | Team 93 | Team 196 | Totals
Saturday, March 15 | 8am-6pm | Maryland University | Workshop | 8 |  |  |  | 0
Sunday, March 16 | 8am-6pm | Maryland University | Workshop | 8 |  |  |  | 0
Monday, March 17 | 7-9pm | Lockheed Martin | Planning Session | 2 |  |  |  | 0
Wednesday, March 19 | 6-9pm | Lockheed Martin | Work Session | 3 |  |  |  | 0
Saturday, March 22 | 10am-1pm | Lockheed Martin | Week 1 Status | 3 |  |  |  | 0
Monday, March 24 | 1-4pm | Lockheed Martin | Work Session | 3 |  |  |  | 0
Wednesday, March 26 | 6-9pm | Lockheed Martin | Work Session | 3 |  |  |  | 0
Friday, March 28 | 1-4pm | Lockheed Martin | Work Session | 3 |  |  |  | 0
Saturday, March 29 | 10am-1pm | Lockheed Martin | Week 2 Status | 3 |  |  |  | 0
Monday, March 31 | 6-9pm | Lockheed Martin | Documentation 1 | 3 |  |  |  | 0
Wednesday, April 2 | 6-9pm | Lockheed Martin | Work Session | 3 |  |  |  | 0
Saturday, April 5 | 10am-1pm | Lockheed Martin | Week 3 Status | 3 |  |  |  | 0
Wednesday, April 9 | 6-9pm | Lockheed Martin | Work Session | 3 |  |  |  | 0
Saturday, April 12 | 10am-1pm | Lockheed Martin | Week 4 Status | 3 |  |  |  | 0
Monday, April 14 | 6-9pm | Lockheed Martin | Documentation 2 | 3 |  |  |  | 0
Wednesday, April 16 | 6-9pm | Lockheed Martin | Work Session | 3 |  |  |  | 0
Saturday, April 19 | 10am-2pm | Lockheed Martin | Week 5 Status | 4 |  |  |  | 0
Monday, April 21 | 6-9pm | Lockheed Martin | Work Session | 3 |  |  |  | 0
Wednesday, April 23 | 5-9pm | Lockheed Martin | Work Session | 4 |  |  |  | 0
Saturday, April 26 | 9am-2pm | Lockheed Martin | Week 6 Status | 5 |  |  |  | 0
Sunday, April 27 | 11am-6pm | Montgomery College Rockville | Scrimmage | 7 |  |  |  | 0
Monday, April 28 | 6-9pm | Lockheed Martin | Documentation Final | 3 |  |  |  | 0
Wednesday, April 30 | 5-9pm | Lockheed Martin | Work Session | 4 |  |  |  | 0
Friday, May 2 | 4-9pm | Lockheed Martin | Tournament Prep | 5 |  |  |  | 0
Saturday, May 3 | 7am-7pm | Maryland University | Tournament | 12 |  |  |  | 0
|  |  |  | 104 | 0 | 0 | 0 | 0