## Flights
Date | Team | Rocket | Flight | Motor/Lot | Weight | Alt | Recovery | Altitude | Time | Comment | Video
2022-01-15 | 1139 | Purple | 1 | F44-8W | 462 | 13 | 22" | 921 | 27 | separation, chute didn't inflate | 2836
2022-01-15 | 1138 | Red | 1 | F44-8W | 452 | 13 | 24" | 681 | 28 | flew badly, lost some data | 2843
2022-01-15 | 1139 | Red | 2 | F44-8W | 455 | 13 | 22" | 456 | 12 | blown igniter, chute deployed too late, crashed | 2856
|  | Conditions | [7 empty] | Target:
|  | Temperature=28F | [7 empty] | 835ft, 41-44sec
Clear skies
Pressure=30.??inHg cloudy
Wind=5-8mph
Altitude=307ft??
Objectives
Fly Red rocket with separation forward from transition at BT80
Red rocket had a 29mm motor mount, but used a 29-24mm converter
Try using F44-8W to reach 835ft.
Lessons
Some concern for altimeter 13
F44 will get us to the 825ft if we keep the weight down
29mm motor mount needs a better converter
Red rocket flew poorly, was it the design of the separation location at the BT80?
Shock cord broke from booster
Parachutes on Purple rocket did not inflate
Actions
Buy more F44-8Ws
Buy a similar 29mm (F23FJ-7)
Buy another converter
Buy more First Fire Jr ignitors
Buy a new transition unit,
Build a new Red rocket with 29mm motor mount
Refurbish the Purple rocket
Make a new BT80 sled for the #13 altimeter
Secure shock cord better in booster
Practice chute packing